## Worksheet
Date | Task | Responsible Person | Risk Identified | Impact Level | Likelihood | Mitigation Plan | Status
2023-10-03 | Project Kickoff Meeting | J. Smith | Poor stakeholder communication | High | Medium | Schedule weekly check-ins with stakeholders. | In Progress
2023-10-04 | Requirements Gathering | A. Johnson | Scope creep due to changing needs | Medium | High | Implement change control board and formal approval process. | Planned
2023-10-06 | Design Phase Review | M. Lee | Dependency on third-party API | High | Medium | Identify backup systems and negotiate SLAs with vendor. | Pending Approval
2023-10-08 | Development Start | T. Brown | Integration issues with legacy systems | High | Medium | Conduct parallel testing and use middleware for data transfer. | At Risk