## Worksheet
Risk Identifier | Risk Description | Risk Category | Likelihood | Impact(th) | Priority Level | Owner | Mitigation Strategy | Response Plan | Monitoring Frequency
R-001 | Project scope creep due to changing stakeholder requirements. | Scope | High | High | Critical | Project Manager | Implement change control board (CCB) approval process. | Require formal sign-off on all scope changes. | Bi-weekly
R-002 | Delays in third-party vendor delivery. | Supply Chain | Medium | High | <High | Procurement Lead | Establish backup vendor list and SLA monitoring. | Escalate if delivery exceeds 5 days. | Weekly
R-003 | Key team member departure. | People | Medium | High | High | HR Manager | Develop cross-training plan and succession strategy. | Conduct role review every 3 months. | Quarterly
R-004 | Budget overruns due to unplanned expenses. | Financial | High | Medium | Medium | Finance Director | Implement budget variance alerts and monthly reviews. | Review expenses weekly with cost control team. | Weekly
R-005 | Security breach in data storage. | Security | Low | Critical | Critical | CISO | Enforce encryption, access controls, and regular audits. | Conduct penetration testing quarterly. | Monthly