## Worksheet
Risk Identifier | Risk Description | Risk Category | Likelihood (1-5) | Impact (1-5) | Risk Priority | Root Cause Analysis | Mitigation Strategy | Responsibility | Timeline (Start-End) | Status | Monitoring Method | Review Date
RISK-001 | Failure of key vendor to deliver critical software components on time. | External Dependencies | 4 | 5 | High (20) | Vendor performance history and contractual penalties. | Establish backup vendor; include penalty clauses in contract. | Project Manager | Q2 Start - Q4 End | Open | Bi-weekly performance reviews with vendor. | 2024-06-15
RISK-002 | Security breach due to outdated system configurations. | Technical Vulnerability | 5 | 4 | High (20) | Lack of regular patching and system audits. | Implement automated patch management and quarterly security audits. | IT Security Officer | Q1 Start - Ongoing | Active | Monthly vulnerability scans and penetration testing. | 2024-07-20
RISK-003 | Key team member resigning before project completion. | Human Resource | 4 | 5 | High (20) | Limited succession planning; low engagement in team. | Develop a talent pool and implement cross-training programs. | HR Lead | Q2 Start - Q4 End | Open | Quarterly staff engagement surveys and retention reviews. | 2024-08-05
RISK-004 | Scope creep leading to budget overruns. | Scope Management | 5 | 5 | Critical (25) | Lack of formal change control procedures. | Implement strict change request process with approval workflow. | Project Sponsor | Ongoing | On Hold | Change log and stakeholder sign-off required for all modifications. | 2024-09-10