## Worksheet
Task | Risk Identified | Impact | Likelihood | Mitigation Strategy | Responsible Person | Due Date | Status
Project Initiation | Scope creep due to stakeholder demands | High | Moderate | Implement a formal change control process and conduct weekly stakeholder reviews | Jane Doe | 2024-03-15 | Pending Review
Requirement Gathering | Incomplete or conflicting requirements | High | ModerateHold cross-functional workshops and validate requirements with stakeholders before finalization | John Smith | 2024-03-25 | In Progress
Design Phase | Limited technical feasibility of proposed solution | Moderate | High | Conduct technical feasibility study and prototype validation prior to final design approval | Alice Johnson | 2024-04-10 | Planned
Development Phase | Delays in third-party integration | Moderate | HighIdentify alternative suppliers and create backup integration plans with contingency timelines | Mike Brown | 2024-05-15 | Pending Approval
Testing Phase | Critical bugs discovered late in cycle | High | ModerateImplement automated testing and introduce a bug bounty system with early detection incentives | Sarah Lee | 2024-06-10 | Not Started