## Worksheet
Risk Item | Description | Probability | Impact | Risk Level | Mitigation Strategy | Owner | Status | Due Date
Scope Creep | Unapproved changes to project scope leading to delays and cost overruns. | Medium | High | High | Establish strict change control process and require approvals. | Project Manager | Active | 2024-05-30
Resource Shortage | Critical team members unavailable due to external commitments. | Low | High | Medium | Cross-train team members and identify backup resources. | HR & Operations Lead | Planned | 2024-06-15
Technology Failure | Critical system downtime affecting project deliverables. | High | Very High | Critical | Implement redundant systems and backup servers. | IT Director | Active | 2024-04-25
Budget Overrun | Unexpected expenses beyond approved project budget. | Medium | Medium | Medium | Conduct monthly cost reviews and adjust allocations. | Finance Manager | Monitor | Ongoing
Stakeholder Misalignment | Conflicting expectations from key stakeholders affecting project direction. | Medium | High | High | Hold regular stakeholder meetings and define clear KPIs. | Project Sponsor | Active | 2024-05-20