## Worksheet
Risk ID | Risk Description | Likelihood | Impact | Risk Score (L x I) | Mitigation Strategy | Owner | Status | Timeline
RISK-001 | Delays in third-party vendor delivery | High | Medium | 6 | Diversify supplier base; establish backup vendors | Project Manager | Active | Q2 2024 - Q3 2024
RISK-002 | Unforeseen regulatory changes | Medium | <High | 12 | Conduct regular compliance audits; maintain legal advisory team | Legal Officer | Monitored | Ongoing
RISK-003 | Scope creep due to stakeholder demands | High | High | 9 | Implement change control board (CCB) process; strict approval workflow | Project Director | Pending Review | Q1 2024 - Q4 2024
RISK-004 | Key team member departure | Medium | High | 6 | Develop cross-training plan; maintain knowledge repository | HR & Leadership Team | Planned Mitigation | Q3 2024
RISK-005 | Technical system failure during go-live | High | Critical | 18 | Conduct full system stress testing; implement failover protocol | IT Head | High Priority | Pre-Go-Live Phase