## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact th> | Risk Score (Likelihood × Impact) | Priority Level | Owner | Mitigation Strategy | Response Plan | Monitoring & Review
RM-001 | Key stakeholder may withdraw support during project execution. | Stakeholder Management | Medium | High | 6 | Prioritized (High) | Jane Doe | Schedule regular stakeholder check-ins and maintain a clear communication plan. | If withdrawal occurs, initiate alternative engagement with backup stakeholders. | Review every bi-weekly; track engagement metrics.
RM-002 | Delays in third-party delivery may impact project timeline. | Supply Chain | High | Medium | 6 | Prioritized (High) | John Smith | Negotiate buffer time and include penalties for late delivery. | If delay occurs, adjust project schedule with resource reallocation. | Monitor delivery status weekly; update risk log accordingly.
RM-003 | Technology stack may become obsolete during development phase. | Technical Risk | Low | Moderate | 3 | Medium | Alex Chen | Evaluate and validate technology alternatives at mid-phase. | If obsolescence occurs, transition to proven, scalable platform with a rollback plan. | Quarterly technology health reviews.