## Worksheet
Task | Responsible Party | Due Date | Risk Level | Mitigation Strategy | Monitoring Frequency | Status
Project Initiation & Feasibility Study | Project Director | 2024-06-15 | Medium | Conduct stakeholder interviews and market analysis. | Bi-weekly | On Track
Scope Definition & Stakeholder Alignment | Project Manager | 2024-07-05 | High | Develop risk register and obtain formal sign-off. | Weekly | In Progress
Resource Allocation & Budget Review | Finance Lead | 2024-07-20 | Medium | Conduct sensitivity analysis on cost vs. risk. | Monthly | Planned
Risk Identification Workshop | Risk Officer | 2024-08-05 | High | Facilitate cross-functional sessions to identify threats and opportunities. | Bi-weekly | Scheduled
Contingency Planning & Response Protocols | Operations Director | 2024-08-25 | Critical | Create detailed escalation and rollback procedures. | Daily (critical risks) | Pending Review