## Worksheet
Project Name | Risk Identification | Risk Description | Likelihood | Impact | Risk Priority | Mitigation Strategy | Responsible Party | Timeline (Month) | Status
Product Launch Phase | Delayed Market Entry | Failure to meet launch deadlines due to supply chain delays. | Medium | High | High | Diversify suppliers; establish backup logistics. | Procurement Manager | Month 3–6 | Active
Product Launch Phase | Negative Public Feedback | Customer backlash due to product design flaws. | Low | High | Medium | Conduct user testing; revise UI/UX based on feedback. | Product Lead | Month 4–7 | Planned
Development Phase | Technical Debt Accumulation | Codebase becomes difficult to maintain over time. | Medium | Medium | Medium | Implement refactoring sprints and code reviews monthly. | Engineering Lead | Ongoing (Monthly) | On Track
Marketing Campaign | Budget Overrun | Unapproved ad spending due to poor forecasting. | High | Medium | High | Implement budget approval gates and real-time monitoring. | Finance Manager | Month 2–12 | Pending Review