## Worksheet
Project Name | Risk Identifier | Risk Description | Likelihood | Impact th> | Risk Score (Likelihood × Impact) | Mitigation Strategy | Owner | Monitoring Frequency | Status
New Client Onboarding Platform | R-001 | System downtime during peak hours due to high user load. | Medium | High | 6 | Implement auto-scaling and load balancing infrastructure. | DevOps Team | Weekly | Active
Market Expansion into EU | R-002 | Regulatory non-compliance due to GDPR violations. | High | Critical | 12 | Conduct legal review and implement data privacy controls. | Legal & Compliance Officer | Bi-weekly | Pending Review
Cloud Migration Project | R-003 | Data loss during migration due to faulty backup procedures. | Medium | High | 6 | Establish automated backup and rollback procedures. | IT Infrastructure Manager | Daily | In Progress