## Worksheet
Risk Item | Risk Description | Likelihood | Impact | Risk Rating | Mitigation Strategy | Owner | Due Date | Status
Scope Creep | Uncontrolled changes to project scope leading to delays and cost overruns. | High | High | Critical | Implement formal change control process and require approval from stakeholders. | Project Manager | 2024-03-15 | Active
Budget Overrun | Exceeding allocated budget due to unforeseen expenses. | Medium | High | High | Monitor budget weekly; establish contingency reserves. | Finance Manager | 2024-03-20 | Active
Resource Shortage | Lack of skilled personnel to complete key project phases. | Medium | Medium | Moderate | Forecast resource needs; cross-train team members and explore external resources. | HR Manager | 2024-04-10 | Planned
Technology Failure | <System downtime or software failure during critical operations. | Low | Critical | Critical | Conduct regular system backups and maintain redundant infrastructure. | IT Director | 2024-03-10 | Resolved