## Worksheet
Task | Responsible | Start Date | End Date | Risk Level | Mitigation Plan | Status
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | Low | Conduct stakeholder workshops and risk identification sessions. | On Track
Requirements Gathering | Business Analyst | 2024-03-16 | 2024-04-10 | Medium | Validate requirements with key stakeholders and document risk registers. | In Progress
Design Phase | Lead Designer | 2024-04-11 | 2024-05-05 | High | Perform security and usability audits; implement fail-safe design patterns. | Planned
Development & Testing | Development Team | 2024-05-06 | 2024-07-15 | High | Implement continuous integration; conduct automated and manual testing cycles. | Not Started
Deployment & Monitoring | IT Operations | 2024-07-16 | 2024-08-31 | Medium | Deploy in staging first; monitor system performance with real-time alerts. | Not Started