## Worksheet
Risk Item | Risk Description | Impact Level | Probability | Risk Rating | Mitigation Strategy | Owner | Response Plan | Monitoring Frequency
Scope Creep | Uncontrolled changes to project scope leading to delays and budget overruns. | High | Medium | High | Implement change control board (CCB) and formal approval process. | Project Manager | All scope changes must be reviewed and approved by CCB before implementation. | Bi-weekly
Resource Shortage | Critical team members unavailable due to unforeseen constraints. | Medium | High | High | Identify backup resources and establish resource pool. | HR & Project Manager | Monitor resource availability monthly and adjust assignments accordingly. | Monthly
Technical Failure | System or software component fails during critical operations. | High | Medium | High | Deploy redundant systems and conduct regular failover testing. | IT Lead | Failover tests performed every quarter. | Quarterly
Budget Overrun | Exceeding approved budget due to unforeseen costs. | High | Medium | High | Establish a contingency reserve and conduct budget reviews at key milestones. | Finance Manager | Monthly budget review and variance analysis. | Monthly
Stakeholder Resistance | Key stakeholders oppose project initiatives due to perceived risks or benefits. | Medium | High | Medium | Conduct stakeholder engagement workshops and clarify project value. | Stakeholder Coordinator | Engagement sessions every three months. | Quarterly