## Worksheet
Project Phase | Risk Identification | Risk Assessment | Mitigation Strategy | Owner | Timeline (Quarter)
Initiation | Scope ambiguity, stakeholder misalignment | Medium – High | Conduct stakeholder workshops and define clear project scope. | Project Manager | Q1
Planning | Resource shortages, budget overruns | High | Develop detailed resource plan and contingency budget. | Finance Lead | Q1–Q2
Execution | Scope creep, team turnover | Medium | Implement change control board and performance monitoring. | Operations Lead | Q2–Q3
Monitoring & Control | Unforeseen dependencies, delays | High – Critical | Conduct bi-weekly risk reviews and update risk register. | Risk Officer | Q3–Q4
Closure | Final deliverables not accepted, compliance issues | Medium | Perform formal acceptance process and audit deliverables. | Project Sponsor | Q4