## Worksheet
Risk Identification | Risk Description | Impact Level | Probability | Mitigation Strategy | Responsible Party | Timeline | Status
R-001 | Delays in vendor delivery of critical components | High | Medium | Establish backup suppliers and maintain safety stock | Procurement Manager | Q1 - Q2 2024 | Active
R-002 | Key team member leaving during project execution | High | Low | Implement cross-training and define knowledge transfer plans | HR & Project Lead | Q3 2024 | Planned
R-003 | Scope creep due to changing client requirements | Medium | High | Enforce change control process and require formal approvals | Project Manager | Ongoing | Monitored
R-004 | Technical failure in core system integration | High | Medium | Conduct regular system stress testing and use redundant architecture | IT Architect | Q2 - Q4 2024 | Active