## Worksheet
Risk Item | Likelihood | Impact | Risk Level | Mitigation Strategy | Owner | Due Date
Budget Overrun | Medium | High | High | Revisit cost estimates; implement change control process. | Finance Manager | 2024-03-15
Key Staff Departure | Low | High | <Medium | Implement training program; establish succession plan. | HR Director | 2024-04-10
Technology Failure | Medium | Medium | Medium | Backup systems in place; regular system updates. | IT Support Lead | 2024-05-01
Client Demand Changes | High | Medium | High | Establish change request process with client approval. | Project Manager | 2024-03-30