## Worksheet
Risk ID | Risk Description | Likelihood | Impact(th) | Risk Priority | Responsibility | Mitigation Strategy | Monitoring Frequency | Status
R-001 | Key team member departure during critical development phase | Medium | High | High Priority | HR & Project Manager | Bonus retention plan, cross-training of backup staff | MonthlyActive
R-002 | Delays in third-party vendor delivery | High | Medium | Medium Priority | Vendor Manager
R-003 | Security breach due to outdated software libraries | Medium | High | High Priority | Quarterly audits, patching schedule, penetration testingMonthlyPending Review
R-004 | Market demand changes before product launch | Low | High | High Priority (Impact only)Product Marketing LeadFlexible go-to-market strategy, customer feedback loopsMonthly | Active
R-005 | Technical debt accumulation leading to performance degradation | HighMediumMedium PriorityEngineering LeadStructured refactoring sprints, automated code reviews | Bi-weekly | Planned