## Worksheet
Risk Item | Risk Description | Probability | Impact | Risk Rating | Mitigation Strategy | Owner | Status
Scope Creep | Unapproved changes to project scope leading to delays and cost overruns. | High | High | Critical | Implement change control process and require formal approvals. | Peter Smith | Open
Resource Shortage | Lack of skilled personnel during key project phases. | Medium | High | High | Early hiring, cross-training, and external resource engagement. | Sarah Johnson | In Progress
Technology Failure | Key software or hardware systems fail during deployment. | HighMedium | Risk Rating: Medium | Mitigation Strategy: Use redundant systems and backup plans. | David Lee | Open
Regulatory Changes | Unexpected changes in laws or compliance requirements. | Medium | Impact: High | Risk Rating: High | Mitigation Strategy: Regular compliance audits and monitoring. | Linda Chen | Planned Review