## Worksheet
Risk Item | Description | Likelihood | Impact> | Risk Score (Likelihood × Impact) | Mitigation Strategy | Owner | Monitoring Frequency | Status
Scope Change | Unapproved modifications to project scope may delay delivery. | High | Medium | 6 | Formal change request process with stakeholder review. | Project Manager | Bi-weekly | Active
Resource Shortage | Key team members unavailable due to external commitments. | Medium | High | 6 | Contingency staffing plan and cross-training. | HR Lead | Monthly | Monitored
Scope Creep | Uncontrolled addition of features beyond original scope. | High | High | 9 | Strict scope control with signed agreements. | Project Sponsor | <Weekly | Critical
Technical Debt Accumulation | Code quality degrades over time due to rushed development. | Medium | Medium | 3 | Regular code reviews and refactoring cycles. | Development Lead | Bi-monthly | Pending Review