## Worksheet
Risk ID | Risk Description | Category | Likelihood | Impact th> | Risk Score | Assigned To | Mitigation Plan | Status | Next Review Date
RISK-001 | Failure of key supplier to deliver on time | Supply Chain | Medium | High | 6 | Jane Smith | Identify backup suppliers; negotiate contracts with SLAs. | Open | 2024-05-15
RISK-002 | Technical system failure during peak usage | Technology | High | Critical | 9 | John Doe | Implement load balancing and redundant servers. | In Progress | 2024-06-10
RISK-003 | Regulatory changes affecting compliance | Legal/Compliance | Medium | High | 6 | Lisa Chen | Conduct quarterly compliance audits; monitor regulatory updates. | Open | 2024-05-30
RISK-004 | Project scope creep due to stakeholder demands | Scope | High | Medium | 7 | Mike Brown | Establish change control board; require formal approval for changes. | Planned | 2024-06-20