## Worksheet
Week | Project Phase | Risk Identified | Risk Level | Probability | Impact | Mitigation Strategy | Owner | Status
1InitiationScope changes during planningHighMediumHighConduct stakeholder workshops and formal change control process.Project ManagerActive
2PlanningBudget overruns due to unforeseen costsMediumHighHighEstablish a contingency reserve and conduct bi-weekly cost reviews.Finance LeadMonitoring
3ExecutionKey team member absenceHighMediumHighIdentify cross-trained backups and update RACI matrix.HR ManagerPending
4Monitoring & ControlScope creep without approvalMediumHighHighEnforce change request process and maintain strict sign-off protocols.Project ManagerActive