## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact th> | Priority | Owner | Mitigation Strategy | Risk Status | Date Identified
R-001 | Failure of critical server during peak usage | Technical | High | High | Critical | IT Manager | Implement redundant servers and load balancing | Active | 2024-03-15
R-002 | Delay in third-party vendor delivery | Supply Chain | Medium | High | High | Procurement Lead | Establish backup vendors and buffer timelines | Monitoring | 2024-03-10
R-003 | Data breach due to outdated software | Security | High | Critical | Critical | CISO | Conduct software patching and security audit | Planned | 2024-03-08
R-004 | Unforeseen regulatory changes | Legal/Compliance | Medium | High | High | Legal Advisor | Monitor regulatory updates and conduct impact analysis | Active | 2024-03-12