## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Risk Score (L×I) | Mitigation Strategy | Responsible Party | Status | Next Review Date
RISK-001 | Failure of key vendor to deliver services on time | Supply Chain | Medium | High | 6 | Identify backup vendors and establish SLAs | Procurement Manager | Active | 2024-06-15
RISK-002 | Data breach due to outdated security protocols | Security | High | Critical | 12 | Conduct system audit, update encryption standards | CISO & IT Security Team | High Priority | 2024-05-30
RISK-003 | Scope creep during project execution | Project Management | Medium | High | 6 | Implement change control board and formal approval process | Project Sponsor | Pending Review | 2024-07-10
RISK-004 | Key team member leaving before project completion | Human Resources | Low | Medium | 3 | Develop succession plan and cross-train team members | HR Manager | Monitored | 2024-08-05