## Worksheet
Date | Project Name | Risk Identified | Likelihood | Impact th> | Risk Level | Mitigation Strategy | Owner | Status
2024-04-01 | Website Redesign Project | Delayed content approval from client | Medium | High | High | Schedule buffer and weekly client check-ins | Jane Doe | Active
2024-04-01 | Mobile App Launch | Server downtime during peak hours | High | Moderate | Moderate | Implement auto-restart scripts and load balancing | John Smith | Pending Review
2024-04-01 | Data Migration Initiative | Data corruption during transfer | Low | High | High | Use checksum validation and backup verification process | Lisa Chen | Under Review