## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Current Status | Ownership | Mitigation Strategy | Response Plan | Last Updated
RISK-001 | Failure of key vendor to deliver on time | Supply Chain | Medium | High | Active | Operations Manager | Identify backup vendors and negotiate SLAs | Escalate to procurement if delivery delay exceeds 5 days | 2024-04-15
RISK-002 | Security breach due to outdated software | Cybersecurity | High | Critical | Urgent Action Required | CISO | Patch all systems; conduct security audit within 7 days | Implement temporary firewall rules until patch deployed | 2024-04-16
RISK-003 | Budget overrun due to scope creep | Financial | Medium | High | Monitored | Project Director | Implement change control process and require approvals | Re-estimate budget quarterly with stakeholder review | 2024-04-10