## Worksheet
Risk ID | Risk Description | Category | Impact Level | Probability | Likelihood Rating | Risk Priority | Owner | Mitigation Strategy | Response Plan | Monitoring Frequency
R-001 | Scope creep leading to budget overruns | Scope | High | Medium | Moderate | High Priority | Project Manager | Establish change control board (CCB) | Review all changes before approval | Bi-weekly
R-002 | Key team member departure | People | Critical | High | Severe | Critical Priority | HR & Project Lead | Cross-train key staff members | Immediate contingency hiring if needed | Monthly
R-003 | Delays in third-party vendor delivery | Supply Chain | Medium | High | Likely | Medium Priority | Procurement Manager | Identify alternative vendors | Weekly status updates with vendor | Bi-weekly
R-004 | Technical failure during system launch | Technology | High | Medium | Moderate | High Priority | IT Lead | Conduct pre-launch stress testing | Implement fallback system and rollback plan | Daily during launch phase