## Worksheet
Risk ID | Risk Description | Risk Category | Probability | Impact th> | Risk Score (P×I) | Owner | Mitigation Strategy | Contingency Plan | Detection Method | Due Date | Status
RISK-001 | Failure of key supplier to deliver components on time | Supply Chain | High | High | 9 | Procurement Manager | Establish backup suppliers and diversify sourcing | Activate alternative supplier within 72 hours of delay notification | Supplier performance monitoring dashboard | 2024-05-15 | Active
RISK-002 | Data breach due to outdated software vulnerabilities | Security | Medium | High | 6 | CISO | Apply patch management protocol and conduct regular audits | Implement emergency data isolation and incident response team activation | Automated vulnerability scanning (bi-weekly) | 2024-06-30 | In Review
RISK-003 | Scope creep during project execution leading to budget overrun | Project Management | High | Medium | 6 | Project Director | Implement strict change control process and require approval from Steering Committee | Initiate cost reallocation and renegotiate scope with stakeholders | Change request logs and stakeholder meetings | 2024-07-10 | Planned
RISK-004 | Unavailability of critical IT infrastructure during peak hours | Technology | Medium | High | 6 | IT Operations Lead | Deploy redundant servers and load balancing systems | Switch to failover cluster within 15 minutes of failure detection | Real-time monitoring with SLA alerts | 2024-08-01 | Pending Action
RISK-005 | Regulatory non-compliance due to incomplete documentation | Compliance | Low | High | 3 | Legal Officer | Standardize documentation templates and conduct compliance training | Conduct internal audit and correct deficiencies within 14 days | Quarterly compliance checklist review | 2024-09-15 | Under Review