## Worksheet
Risk Identifier | Risk Description | Impact Level | Likelihood | Risk Rating (Impact × Likelihood) | Mitigation Strategy | Responsible Party | Timeline | Monitoring Frequency | Status
RISK-001 | Project delay due to vendor failure | High | Medium | Moderate (4) | Identify backup vendors and negotiate SLAs | Project Manager | Q2 2024 | Bi-weekly | Active
RISK-002 | Budget overrun due to scope creep | High | High | Critical (8) | Implement change control process and cost tracking | Finance Lead | Ongoing | Weekly | Open
RISK-003 | Technical integration failure | Medium | High | High (6) | Conduct thorough system testing and conduct UAT | Lead Developer | Q4 2024 | Monthly | Planned
RISK-004 | Key team member departure | High | Medium | Moderate (4) | Cross-train team members and establish succession plan | HR & Project Manager | Q1 2025 | Quarterly | Pending Review
RISK-005 | Regulatory compliance failure | Critical | Medium | High (6) | Conduct legal review and update policies | Legal Counsel | Ongoing | Monthly | Active