## Worksheet
Risk ID | Risk Description | Likelihood | Impact-th> | Risk Score | Assigned To | Status | Mitigation Plan | Last Updated
RISK-001 | Project timeline delay due to unexpected vendor issues | Medium | High | 7 | Jane Smith | Active | Engage backup vendor; implement buffer time in schedule. | 2024-03-15
RISK-002 | Key team member leaving mid-project | High | Medium | 8 | Mike Johnson | Pending Review | Identify and onboard a replacement; document critical knowledge. | 2024-03-10
RISK-003 | Security breach due to outdated software | Medium | High | 9 | Sarah Lee | In Progress | Update software; conduct vulnerability scan and patch. | 2024-03-08
RISK-004 | Client scope changes after launch | Low | High | 5 | David Chen | Planned | Document scope change process; require formal approval. | 2024-03-05