## Worksheet
Risk Identification | Risk Description | Impact Level | Likelihood | Risk Priority (Impact × Likelihood) | Mitigation Strategy | Responsible Party | Timeline | Status
1 | Scope creep due to stakeholder demands | High | Medium | 6 | Implement change control process and require formal approvals | Project Manager | Ongoing | Active
2 | Delays in vendor delivery | Medium | <High | 6 | Establish alternative suppliers and buffer timelines | Procurement Lead | Q3 2024 | Active
3 | Budget overrun due to unexpected costs | High | Medium | 6 | Conduct monthly budget reviews and cost tracking | Finance Manager | Monthly Review | Monitoring
4 | Technical failure in core system integration | Critical | Low | 3 | Develop backup integration protocol and conduct stress testing | IT Director | Pre-Qualification Phase | Planned