## Worksheet
Risk Identification | Risk Description | Likelihood | Impact | Risk Rating | Mitigation Strategy | Responsibility | Monitoring Frequency
1 | Project scope may change mid-development. | High | Medium | Medium-High | Establish clear change control process and approval workflows. | Project Manager | Monthly
2 | Key team member may become unavailable. | Medium | High | High | Develop backup staff plan and cross-train key personnel. | HR & Team Lead | Quarterly
3 | Delays in client deliverables may occur. | High | High | Very High | Improve scheduling and set buffer timelines for critical phases. | Project Manager | Bi-weekly
4 | Client requirements may be unclear or change late. | Medium | High | High | Conduct detailed discovery sessions and formal sign-off on requirements. | Business Analyst | Bi-weekly