## Worksheet
Risk Identification | Risk Description | Likelihood | Impact th> | Risk Rating (Likelihood × Impact) | Mitigation Strategy | Owner | Due Date | Status
1 | Scope creep due to stakeholder demands | High | Medium | 6 | Implement change control board and formal approval process | Project Manager | 2024-05-30 | Open
2 | Delays in third-party vendor delivery | Medium | High | 6 | Establish backup vendors and monitor SLAs closely | Procurement Lead | 2024-06-15 | In Progress
3 | Technology obsolescence during project lifecycle | <Low | High | 3 | Conduct technology review every 6 months | Tech Manager | 2024-07-31 | Planned
4 | Resource unavailability (key team member leaving) | High | High | 9 | Implement cross-training and backup staffing plan | HR & Project Lead | 2024-05-10 | Open