## Worksheet
Risk Item | Risk Description | Likelihood | Impact th> | Risk Rating (Likelihood × Impact) | Mitigation Strategy | Owner | Status | Next Review Date
Scope Creep | Unapproved changes to project scope may delay delivery. | Medium | High | High | Implement change control board (CCB) approval process. | Jane Smith | Active | 2024-05-31
Resource Shortage | Critical team members may be unavailable due to overallocation. | High | Medium | High | Review resource plans and reallocate tasks weekly. | Michael Johnson | Active | 2024-06-15
Technology Failure | Core system may fail during peak usage. | Medium | High | High | Implement redundant servers and backup systems. | Sarah Lee | Pending Review | 2024-06-10
Stakeholder Resistance | Key stakeholders may oppose project changes. | Low | High | Moderate | Conduct early engagement sessions and communication plan. | David Brown | Planned | 2024-05-30