## Worksheet
Risk Identification | Risk Description | Likelihood | Impact th> | Risk Rating (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Timeline | Status
1 | Project scope changes without formal approval | Medium | High | 6 (Medium × High) | Implement change control process and require formal request form | Project Manager | Ongoing | Open
2 | Delays in vendor delivery | High | Medium | 6 (High × Medium) | Schedule buffer and alternate supplier identification | Procurement Lead | Q3 2024 | Open
3 | Key team member leaving unexpectedly | Medium | High | 6 (Medium × High) | Create cross-training plan and maintain backup contacts | HR & Team Lead | Ongoing | Open
4 | Scope creep due to stakeholder demands | High | High | 9 (High × High) | Conduct regular stakeholder reviews and set clear boundaries | Project Manager | Monthly | Open