## Worksheet
Risk Identifier | Risk Description | Risk Category | Likelihood | Impact th> | Priority Level | Mitigation Strategy | Responsible Party | Timeline | Status
RISK-001 | Key vendor may delay delivery of critical components. | Supply Chain | Medium | High | High | Identify backup vendors and negotiate early delivery terms. | Procurement Manager | Q2 2024 | Active
RISK-002 | Scope changes during project execution may affect delivery timelines. | Scope Management | <HighMedium | High | High | Implement a formal change control process and regular stakeholder reviews. | Project Manager | Ongoing | Open
RISK-003 | Unforeseen technical issues during system integration. | Technical | Low | Critical | High | Conduct thorough technical testing and allocate contingency resources. | Engineering Lead | Q3 2024 | Planned
RISK-004 | Regulatory changes may require compliance adjustments. | Compliance | Medium | High | Medium | Monitor regulatory updates and conduct compliance audits quarterly. | Legal Advisor | Ongoing | Active