## Worksheet
Risk Identification | Risk Description | Likelihood | Impact | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Response Plan | Monitoring & Review
Technical Failure | Critical system component may fail during operation. | High | High | 9 | Implement redundancy and regular system health checks. | IT Operations Team | Automated alerts and failover procedures. | Weekly review by engineering lead.
Scope Creep | Project requirements may expand beyond original scope. | Medium | High | 6 | Enforce change control process and formal approvals. | Project Manager | All scope changes require stakeholder sign-off. | Bi-weekly review with steering committee.
Budget Overrun | Costs may exceed the allocated project budget. | High | Medium | 6 | Monthly financial audits and cost tracking. | Finance Manager | Set budget triggers for escalation. | Monthly review with finance and PMO.
Resource Shortage | Key team members may be unavailable due to illness or transfer. | Medium | Medium | 3 | Cross-train team members and maintain a backup roster. | HR & Project Manager | Immediate reallocation of tasks if needed. | Monthly resource planning meeting.
Compliance Failure | Failure to meet regulatory or legal requirements. | Low | High | 3 | Conduct regular compliance audits and training. | Legal & Compliance Officer | Quarterly compliance review and reporting. | Annual internal audit by external consultant.