## Worksheet
Activity | Start Date | End Date | Responsible Party | Risk Level | Mitigation Strategy | Status
Risk Identification Workshop | 2024-03-01 | 2024-03-05 | Project Steering Committee | Medium | Conduct stakeholder interviews and use risk matrix. | In Progress
Risk Assessment & Prioritization | 2024-03-06 | 2024-03-15 | Risk Management Team | High | Quantitative analysis using scenario modeling. | Planned
Develop Contingency Plans | 2024-03-16 | 2024-04-10 | Project Manager & SMEs | Critical | Define fallback actions for key risks. | Scheduled
Monitor & Review Risks Weekly | 2024-03-01 | Ongoing | Risk Management Office | Medium | Hold weekly risk review meetings and update dashboard. | Active