## Worksheet
Task | Start Date | End Date | Responsible Party | Risk Level | Status
Risk Identification Workshop | 2024-03-01 | 2024-03-05 | Project Manager | Medium | Completed
Risk Assessment & Prioritization | 2024-03-06 | 2024-03-15 | Risk Analyst Team | High | In Progress
Mitigation Strategy Development | 2024-03-16 | 2024-04-10 | Project Team | High | Planned
Risk Monitoring & Review Meetings | 2024-04-11 | 2024-06-30 | Project Manager & Team | Medium | Scheduled
Contingency Plan Finalization | 2024-05-01 | 2024-05-15 | Risk Office | Critical | In Progress