## Worksheet
Task | Start Date | End Date | Responsible Person | Risk Level | Mitigation Strategy | Status
Risk Identification Workshop | 2024-03-01 | 2024-03-05 | Jane Smith | Medium | Conduct cross-functional sessions with stakeholders. | In Progress
Risk Assessment & Prioritization | 2024-03-06 | 2024-03-10 | John Doe | High | Use quantitative and qualitative scoring models. | Planned
Risk Register Development | 2024-03-11 | 2024-03-15 | Lisa Chen | Medium | Document all identified risks with impact and likelihood. | Pending Approval
Contingency Planning | 2024-03-16 | 2024-03-25 | Robert Kim | High | Develop recovery plans and fallback options. | Not Started
Risk Monitoring & Review | 2024-03-26 | 2024-06-30 | Project Office Team | Ongoing | Bi-weekly reviews with stakeholders and risk owners. | Scheduled