## Worksheet
Activity | Start Date | End Date | Responsible Party | Risk Level | Mitigation Strategy
Risk Identification Workshop | 2024-03-15 | 2024-03-18 | Project Manager & Stakeholders | Medium | Conduct structured sessions with cross-functional teams; document risks in shared risk register.
Threat Assessment & Vulnerability Analysis | 2024-03-20 | 2024-03-25 | Security Officer & IT Team | High | Perform penetration testing; review system logs and access controls.
Contingency Plan Development | 2024-04-01 | 2024-04-10 | Project Director & Risk Officer | Medium-High | Define recovery procedures for critical system failures and data loss.
Risk Review & Status Update Meeting | 2024-04-15 | 2024-04-15 | Steering Committee | Low | Review updated risk register and validate mitigation effectiveness.
Third-Party Risk Evaluation | 2024-05-01 | 2024-05-15 | Legal & Compliance Team | Medium | Audit vendor contracts and ensure compliance with data protection standards.