## Worksheet
Activity | Start Date | End Date | Responsible Party | Risk Identified | Mitigation Strategy | Status
Risk Assessment Planning | 2024-01-15 | 2024-01-30 | Project Manager | Identify key risks in project scope | Conduct stakeholder interviews and SWOT analysis | In Progress
Risk Categorization & Prioritization | 2024-02-01 | 2024-02-15 | Risk Analyst | Operational, financial, technical risks | Apply risk matrix (likelihood vs. impact) | Planned
Contingency Planning | 2024-02-16 | 2024-03-10 | Operations Lead | Supply chain disruption | Establish backup suppliers and inventory buffer | Not Started
Risk Monitoring & Review | 2024-03-11 | 2024-06-30 | Project Office Team | Ongoing environmental changes | Monthly risk review meetings and reporting | Planned