## Worksheet
Task | Start Date | End Date | Responsible Party | Risk Level | Mitigation Strategy | Monitoring Frequency | Critical Path?
Risk Identification Workshop | 2024-03-01 | 2024-03-05 | Project Manager & Risk Officer | High | Conduct stakeholder interviews and use FMEA technique. | Bi-weekly | Yes
Risk Assessment & Prioritization | 2024-03-06 | 2024-03-15 | Risk Analyst Team | Medium | Apply quantitative scoring (Likelihood × Impact). | Weekly | Yes
Develop Risk Response Plan | 2024-03-16 | 2024-04-05 | Risk Management Office | High | Assign owners, define actions, set thresholds. | Monthly | Yes
Risk Monitoring & Review Meetings | 2024-04-06 | 2024-12-31 | Project Steering Committee | Ongoing | Track open risks, evaluate effectiveness of controls. | Quarterly | Yes
Contingency Planning & Escalation Protocol | 2024-05-01 | 2024-06-30 | Crisis Management Team | Critical | Define escalation paths and fallback scenarios. | Bi-weekly | Yes