## Worksheet
Task | Start Date | End Date | Responsible Employee | Status | Risk Level | Mitigation Plan
Identify Key Risks | 2024-03-15 | 2024-03-25 | Sarah Johnson | In Progress | Medium | Conduct stakeholder interviews and risk workshops.
Assess Impact & Likelihood | 2024-03-26 | 2024-04-05 | Michael Chen | Not Started | High | Use risk matrix to evaluate impact and likelihood.
Develop Risk Response Strategies | 2024-04-06 | 2024-04-18 | Lisa Rodriguez | Not Started | Medium | Create action plans for top 5 risks.
Monitor and Review Risks Weekly | 2024-04-19 | Ongoing | Team Lead | Not Started | Low | Hold weekly risk review meetings and update dashboard.
Document Final Risk Register | 2024-05-10 | 2024-05-15 | All Team Members | Not Started | Low | Compile all findings and submit for approval.