## Worksheet
Task | Start Date | End Date | Responsible Party | Risk Level | Mitigation Strategy | Status | Dependencies
Risk Assessment Planning | 2024-03-01 | 2024-03-15 | Project Manager | Medium | Conduct stakeholder interviews and use risk matrix. | On Track | None
Identify Key Risks | 2024-03-16 | 2024-03-31 | Risk Analyst | High | Use historical data and SWOT analysis. | In Progress | Risk Assessment Planning
Develop Risk Mitigation Plans | 2024-04-01 | 2024-04-30 | Project Team | Medium | Assign ownership, create contingency plans. | Not Started | Key Risk Identification
Monitor and Review Risks | 2024-05-01 | 2024-06-30 | Risk Officer | Low to Medium | Weekly risk review meetings and dashboard updates. | Planned | Mitigation Plans in Place
Escalate Critical Risks | 2024-05-15 | 2024-06-30 | Project Sponsor | High | Formal escalation process to Steering Committee. | Not Started | Risk Monitoring Phase