## Worksheet
Activity | Start Date | End Date | Responsible Party | Risk Identified | Impact (Financial) | Mitigation Strategy | Status
Project Initiation & Feasibility Study | 2024-03-01 | 2024-03-15 | Project Director | Market volatility risk | $50,000 | Conduct sensitivity analysis and diversify investment sources. | On Track
Budget Finalization & Risk Assessment | 2024-03-16 | 2024-04-10 | Finance Manager | Cost overruns due to inflation | $75,000 | Implement fixed-price contracts and adjust forecasts monthly. | On Track
Resource Allocation & Team Setup | 2024-04-11 | 2024-05-05 | HR & Operations Lead | Key personnel turnover risk | $60,000 | Establish retention plans and cross-train team members. | On Track
Development & Implementation Phase | 2024-05-06 | 2024-08-31 | Project Manager & Tech Lead | Technical failure or delay in delivery | $150,000 | Adopt agile methodology with weekly review checkpoints and backup systems. | Planned
Performance Review & Risk Monitoring | 2024-09-01 | 2024-10-31 | Risk Officer | Regulatory changes impacting compliance | $80,000 | Engage legal and compliance teams for early alerts and scenario planning. | Pending Review