## Worksheet
Project Timeline - Risk Management (Home Use)
Phase | Start Date | End Date | Main Activities | Risks Identified | Risk Mitigation Strategy th>
Initiation | 2024-01-15 | 2024-01-31 | Define project scope, stakeholders, objectives | Scope ambiguity, stakeholder misalignment | Conduct workshops with key stakeholders; document shared vision
Planning | 2024-02-01 | 2024-03-15 | Create risk register, project schedule, resource plan | Incomplete risk assessment, poor estimation techniques | Apply probabilistic analysis; include buffer time in critical path
Execution | 2024-03-16 | 2024-06-30 | Implement project deliverables, manage team tasks | Resource shortages, scope creep | Monitor resource allocation weekly; enforce change control process
Monitoring & Control | 2024-07-01 | 2024-09-30 | Track risks, update risk register, adjust plans | Lack of timely risk reporting, communication gaps | Automate status reports; schedule weekly review meetings
Closure | 2024-10-01 | 2024-10-31 | Finalize documentation, conduct project review, release resources | Unresolved legacy risks, data loss concerns | Perform post-mortem review; archive all risk-related records securely