## Worksheet
Task | Start Date | End Date | Responsible | Status | Risk Level | Mitigation Plan
Risk Assessment Planning | 2024-03-01 | 2024-03-15 | Jane Smith | On Track | Medium | Conduct stakeholder interviews and document key risks.
Identify Critical Risks | 2024-03-16 | 2024-04-01 | Mark Johnson | On Track | High | Develop a risk register and prioritize top 5 threats.
Risk Monitoring & Review | 2024-04-02 | 2024-06-30 | Sarah Lee | Planned | Medium | Hold bi-weekly review meetings with team and update risk register.
Contingency Planning | 2024-05-01 | 2024-05-31 | David Kim | Pending | High | Define response strategies for top risks including escalation paths.
Final Risk Validation | 2024-07-01 | 2024-07-15 | Project Steering Committee | Not Started | Low | Validate final risk list and mitigation plans with stakeholders.