## Worksheet
Task | Start Date | End Date | Responsible Person | Risk Level | Mitigation Strategy | Status
Risk Assessment Planning | 2024-03-01 | 2024-03-15 | Jane Smith | Medium | Conduct stakeholder workshops and identify key risks. | On Track
Identify Critical Assets | 2024-03-16 | 2024-03-31 | Mark Johnson | High | Map physical and digital assets with vulnerability analysis. | In Progress
Develop Risk Response Plan | 2024-04-01 | 2024-04-30 | Lisa Chen | High | Define controls, escalation paths, and contingency actions. | Planned
Monitor and Review Risks | 2024-05-01 | 2024-05-31 | David Brown | Medium | Conduct monthly reviews and update risk register. | Not Started