## Worksheet
Task | Start Date | End Date | Responsible Person | Risk Level | Mitigation Strategy | Status
Risk Assessment Planning | 2024-03-01 | 2024-03-15 | John Doe | Medium | Conduct stakeholder interviews and document risk inventory. | In Progress
Identify Key Risks | 2024-03-16 | 2024-03-31 | Jane Smith | High | Use SWOT and scenario analysis to evaluate potential risks. | Not Started
Risk Prioritization & Analysis | 2024-04-01 | 2024-04-15 | Mike Johnson | High | Apply risk scoring model (Likelihood × Impact). | Planned
Develop Contingency Plans | 2024-04-16 | 2024-05-01 | Lisa Brown | Medium | Create alternative action plans for top 5 risks. | Not Started
Monitor & Review Risks | 2024-05-02 | 2024-10-31 | Team Lead | Ongoing | Weekly risk review meetings and updates. | Planned