## Worksheet
Task | Start Date | End Date | Responsible | Risk Level | Mitigation Strategy | Status
Risk Assessment Planning | 2024-03-01 | 2024-03-15 | John Smith | Medium | Conduct stakeholder interviews and review historical data. | On Track
Identify Key Risks | 2024-03-16 | 2024-03-31 | Sarah Lee | High | Use risk matrix and scenario analysis. | In Progress
Risk Prioritization | 2024-04-01 | 2024-04-15 | Michael Chen | High | Apply impact and likelihood scoring. | Planned
Develop Mitigation Plans | 2024-04-16 | 2024-05-10 | Emily Wong | Medium | Create action plans and assign owners. | Pending Approval
Monitor & Review Risks | 2024-05-11 | 2024-06-30 | David Kim | Low | Hold biweekly review meetings. | Scheduled